## Gantt
[PROJECT NAME] - Project Management Gantt Chart Excel Template | [21 empty] | Project Manager : | [5 empty] | [Project Manager] | [8 empty] | [Company Name]
| Input column | [5 empty] | Project start date: | [5 empty] | 2021-08-30 | [26 empty] | 1
Calculated column
[7 empty] | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44
 | time axis 2021-08-30 to 2021-10-29
TYPE | TASK NAME | START DATE | WORK DAYS | END DATE | TEAM MEMBER | % | time axis 2021-08-30 to 2021-10-29
P | Phase 1 | 2021-08-30 | 32 | 2021-10-12
T | Task 01 | 2021-08-30 | 10 | 2021-09-10 | Team Member | 100%
T | Task 02 | 2021-09-13 | 3 | 2021-09-15 | Team Member | 35%
T | Task 03 | 2021-09-16 | 3 | 2021-09-20 | Team Member
T | Task 04 | 2021-09-17 | 5 | 2021-09-23 | Team Member | 60%
T | Task 05 | 2021-09-24 | 3 | 2021-09-28 | Team Member
T | Task 06 | 2021-09-26 | 5 | 2021-09-30 | Team Member | 40%
T | Task 07 | 2021-10-01 | 2 | 2021-10-04 | Team Member
T | Task 08 | 2021-10-05 | 2 | 2021-10-06 | Team Member | 50%
T | Task 09 | 2021-10-07 | 4 | 2021-10-12 | Team Member
P | Phase 2 | 2021-09-24 | 23 | 2021-10-26
T | Task 10 | 2021-09-24 | 5 | 2021-09-30 | Team Member
T | Task 11 | 2021-09-30 | 6 | 2021-10-07 | Team Member | 20%
T | Task 12 | 2021-10-06 | 4 | 2021-10-11 | Team Member
T | Task 13 | 2021-10-12 | 6 | 2021-10-19 | Team Member
T | Task 14 | 2021-10-20 | 2 | 2021-10-21 | Team Member
T | Task 15 | 2021-10-22 | 3 | 2021-10-26 | Team Member
P | Phase 3 | 2021-10-11 | 15 | 2021-10-29
T | Task 16 | 2021-10-11 | 2 | 2021-10-12 | Team Member
T | Task 17 | 2021-10-13 | 3 | 2021-10-15 | Team Member
T | Task 18 | 2021-10-18 | 2 | 2021-10-19 | Team Member
T | Task 19 | 2021-10-20 | 3 | 2021-10-22 | Team Member
T | Task 20 | 2021-10-25 | 1 | 2021-10-25 | Team Member
T | Task 21 | 2021-10-26 | 3 | 2021-10-28 | Team Member
T | Task 22 | 2021-10-28 | 2 | 2021-10-29 | Team Member

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (P3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TYPE, TASK NAME, START DATE, the number of WORKDAYS, and TEAM MEMBER.
|  |  | Note: | Type can be Phase (P) or Task (T).
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 29), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AW-BA)
|  |  | Step 2: | Select the column after the last date (BB), then right click and select Insert Copied Cells.
Calculation for END DATE
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.
|  |  | Note: | Do not enter end dates manually since the END DATE is a calculated column.
Calculation for Phases
| • | You can enter the start date and number of workdays of a Phase manually.
| • | However, if you want to do calculation automatically based on its tasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_tasks_start_dates)
|  |  | WORK DAYS |  | =IF(ISBLANK(phase_start_date),"",NETWORKDAYS(phase_start_date,MAX(range_of_its_tasks_end_dates)))