## Gantt
[PROJECT NAME] - Gantt Chart Excel Template with Dependencies | [24 empty] | Project Manager : | [5 empty] | [Project Manager] | [8 empty] | [Company Name]
| Input column | [8 empty] | Project start date: | [5 empty] | 2021-08-30 | [26 empty] | 1
Calculated column
[10 empty] | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44
 | time axis 2021-08-30 to 2021-10-29
ID | TYPE | TASK NAME | IND. START DATE | WORK DAYS | DEPENDENCY | START DATE | END DATE | TEAM MEMBER | % | time axis 2021-08-30 to 2021-10-29
1 | P | Phase 1 | 2021-08-30 | 32 |  | 2021-08-30 | 2021-10-12
2 | T | Task 01 | 2021-08-30 | 13 |  | 2021-08-30 | 2021-09-15 | Team Member
3 | S | Subtask 1 | 2021-08-30 | 8 |  | 2021-08-30 | 2021-09-08 | Team Member | 80%
4 | S | Subtask 2 | 2021-09-06 | 5 | 3 | 2021-09-09 | 2021-09-15 | Team Member | 50%
5 | T | Task 02 | 2021-09-13 | 3 |  | 2021-09-13 | 2021-09-15 | Team Member
6 | T | Task 03 | 2021-09-16 | 3 |  | 2021-09-16 | 2021-09-20 | Team Member
7 | T | Task 04 | 2021-09-17 | 5 | 6 | 2021-09-21 | 2021-09-27 | Team Member | 60%
8 | T | Task 05 | 2021-09-24 | 3 |  | 2021-09-24 | 2021-09-28 | Team Member
9 | T | Task 06 | 2021-09-26 | 5 |  | 2021-09-26 | 2021-09-30 | Team Member | 40%
10 | T | Task 07 | 2021-10-01 | 2 | 9 | 2021-10-01 | 2021-10-04 | Team Member
11 | T | Task 08 | 2021-10-05 | 2 |  | 2021-10-05 | 2021-10-06 | Team Member | 50%
12 | T | Task 09 | 2021-10-07 | 4 |  | 2021-10-07 | 2021-10-12 | Team Member
13 | P | Phase 2 | 2021-09-24 | 23 |  | 2021-09-24 | 2021-10-26
14 | T | Task 10 | 2021-09-24 | 5 |  | 2021-09-24 | 2021-09-30 | Team Member
15 | T | Task 11 | 2021-09-30 | 6 |  | 2021-09-30 | 2021-10-07 | Team Member
16 | T | Task 12 | 2021-10-06 | 4 |  | 2021-10-06 | 2021-10-11 | Team Member
17 | T | Task 13 | 2021-10-12 | 6 |  | 2021-10-12 | 2021-10-19 | Team Member
18 | T | Task 14 | 2021-10-20 | 2 |  | 2021-10-20 | 2021-10-21 | Team Member
19 | T | Task 15 | 2021-10-22 | 3 |  | 2021-10-22 | 2021-10-26 | Team Member
20 | P | Phase 3 | 2021-10-11 | 15 |  | 2021-10-11 | 2021-10-29
21 | T | Task 16 | 2021-10-11 | 2 |  | 2021-10-11 | 2021-10-12 | Team Member
22 | T | Task 17 | 2021-10-13 | 3 |  | 2021-10-13 | 2021-10-15 | Team Member
23 | T | Task 18 | 2021-10-18 | 8 |  | 2021-10-18 | 2021-10-27 | Team Member
24 | T | Task 19 | 2021-10-20 | 3 |  | 2021-10-20 | 2021-10-22 | Team Member
25 | T | Task 20 | 2021-10-25 | 1 |  | 2021-10-25 | 2021-10-25 | Team Member
26 | T | Task 21 | 2021-10-26 | 3 |  | 2021-10-26 | 2021-10-28 | Team Member
27 | T | Task 22 | 2021-10-28 | 2 |  | 2021-10-28 | 2021-10-29 | Team Member
28

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (P3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TYPE, TASK NAME, IND. START DATE, the number of WORKDAYS, and TEAM MEMBER.
|  |  | Note: | Type can be Phase (P), Task (T), or Subtask (S).
The IND. START DATE (independent start date) is the start date without dependency.
ID is unique and calculated automatically.
START DATE and END DATE are calculated columns. Please do not enter values manually into these columns.
The bars are based on START DATE and END DATE.
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 36), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AZ-BD)
|  |  | Step 2: | Select the column after the last date (BE), then right click and select Insert Copied Cells.
The calculation for START DATE and END DATE
| • | If you enter an IND. START DATE, by default, the START DATE and END DATE are filled in with the same values as the IND. START DATE.
| • | Do not enter START DATE and END DATE values manually since both are calculated columns.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.
How to add Dependency
| • | Use dependency if you have an item (task/subtask/phase) that starts only after another item ends.
| • | Each item (phase/tasks/subtask) has a unique ID.
| • | To add the dependency, use a cell reference instead of entering the predecessor's ID manually.
As shown in the Gantt worksheet, suppose you have Task 04 with ID=7,and it's dependent on Task 03 with ID=6 (ID=6 is in cell B14).
To add the dependency: Enter "=B14" in the DEPENDENCY column of Task 04.
The start date of Task 04 will be automatically updated based on Task 03's end date.
The calculation for Phases
| • | You can enter the start date and number of workdays of a Phase manually.
| • | However, if you want to do calculation automatically based on its tasks, use the following formulas:
|  |  | IND. START DATE |  | =MIN(range_of_its_tasks_start_dates)
|  |  | WORK DAYS |  | =IF(ISBLANK(phase_start_date),"",NETWORKDAYS(phase_start_date,MAX(range_of_its_tasks_end_dates)))
The calculation for Tasks
| • | You can enter the start date, the number of workdays, and % completion of a Task manually.
| • | However, if you want to do calculation automatically based on its subtasks, use the following formulas:
|  |  | IND. START DATE |  | =MIN(range_of_its_subtasks_start_dates)
|  |  | WORKDAYS |  | =IF(ISBLANK(task_start_date),"",NETWORKDAYS(task_start_date,MAX(range_of_its_subtasks_end_dates)))
|  |  | % |  | =SUMPRODUCT(range_of_its_subtasks_workdays,range_of_its_subtasks_%completed/SUM(range_of_its_subtasks_workdays)