## Gantt
[PROJECT NAME] - Construction Gantt chart Excel template | [23 empty] | Project Manager : | [5 empty] | [Project Manager] | [8 empty] | [Company Name]
| Input column | [7 empty] | Project start date: | [5 empty] | 2021-08-30 | [25 empty] | 1
Calculated column
[9 empty] | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44
 | time axis 2021-08-30 to 2021-10-29
TYPE | TASK NAME | START DATE | WORK DAYS | END DATE | RESOURCE | % | ESTIMATED COST | ACTUAL COST | time axis 2021-08-30 to 2021-10-29
P | Architectural design | 2021-08-30 | 11 | 2021-09-13
T | Prepare construction document | 2021-08-30 | 10 | 2021-09-10 | Bob | 100%
T | Sign agreement with client | 2021-09-10 | 2 | 2021-09-13 | Alex | 100% | 80000 | 90000
P | Construction | 2021-09-15 | 11 | 2021-09-29
T | Foundation | 2021-09-15 | 11 | 2021-09-29 | Bob | 50%
S | Excavation | 2021-09-15 | 5 | 2021-09-21 | Alex | 80% | 80000 | 90000
S | Form footings | 2021-09-21 | 4 | 2021-09-24 | John | 30%
S | Place rebar | 2021-09-24 | 3 | 2021-09-28
S | Place concrete | 2021-09-29 | 1 | 2021-09-29
T | First floor | 2021-09-30 | 7 | 2021-10-08
S | Walls | 2021-09-30 | 6 | 2021-10-07
S | Windows and doors | 2021-10-05 | 4 | 2021-10-08
T | Second floor | 2021-10-11 | 10 | 2021-10-22
S | Walls | 2021-10-11 | 6 | 2021-10-18
S | Windows and doors | 2021-10-19 | 4 | 2021-10-22
T | Roof | 2021-10-25 | 5 | 2021-10-29
S | Roof structure | 2021-10-25 | 2 | 2021-10-26
S | Install water retention facilities | 2021-10-27 | 3 | 2021-10-29

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (P3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TYPE, TASK NAME, START DATE, the number of WORKDAYS, RESOURCE, and ESTIMATED COST.
|  |  | Note: | Type can be Phase (P), Task (T), or Subtask (S).
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 36), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AY-BC)
|  |  | Step 2: | Select the column after the last date (BD), then right-click and select Insert Copied Cells.
The calculation for END DATE
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.
|  |  | Note: | Do not enter end dates manually since the END DATE is a calculated column.
The calculation for Phases
| • | You can enter the start date and number of workdays of a Phase manually.
| • | However, if you want to do calculation automatically based on its tasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_tasks_start_dates)
|  |  | WORK DAYS |  | =IF(ISBLANK(phase_start_date),"",NETWORKDAYS(phase_start_date,MAX(range_of_its_tasks_end_dates)))
The calculation for Tasks
| • | You can can enter the start date, number of workdays, and % completion of a tasks manually.
| • | However, if you want to do calculation automatically based on its subtasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_subtasks_start_dates)
|  |  | WORKDAYS |  | =IF(ISBLANK(task_start_date),"",NETWORKDAYS(task_start_date,MAX(range_of_its_subtasks_end_dates)))
|  |  | % |  | =SUMPRODUCT(range_of_its_subtasks_workdays,range_of_its_subtasks_%completed/SUM(range_of_its_subtasks_workdays)