## Gantt
[PROJECT NAME] - Event Planning Gantt Chart Excel Template | [20 empty] | Project Manager : | [5 empty] | [Project Manager] | [8 empty] | [Company Name]
| Input column |  |  |  |  | Project start date: | [5 empty] | 2021-08-30 | [26 empty] | 1
Calculated column
[6 empty] | WEEK 36 |  |  |  |  | WEEK 37 |  |  |  |  | WEEK 38 |  |  |  |  | WEEK 39 |  |  |  |  | WEEK 40 |  |  |  |  | WEEK 41 |  |  |  |  | WEEK 42 |  |  |  |  | WEEK 43 |  |  |  |  | WEEK 44
 | time axis 2021-08-30 to 2021-10-29
TYPE | TASK NAME | START DATE | WORK DAYS | END DATE | % | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
P | Invitation | 2021-08-30 | 5 | 2021-09-03
T | List attendee names | 2021-08-30 | 3 | 2021-09-01 | 100%
T | Create invitations | 2021-09-02 | 2 | 2021-09-03 | 100%
T | Review and send invitations | 2021-09-03 | 1 | 2021-09-03 | 100%
P | Book meeting space and hotel rooms | 2021-09-06 | 5 | 2021-09-10
T | Book hotel rooms for speakers | 2021-09-06 | 3 | 2021-09-08 | 100%
T | Book hotel rooms for special guests | 2021-09-08 | 2 | 2021-09-09 | 100%
T | Book meeting space | 2021-09-10 | 1 | 2021-09-10 | 100%
P | Preparations | 2021-09-13 | 7 | 2021-09-21
T | Prepare equipments for presentations | 2021-09-13 | 4 | 2021-09-16 | 50%
T | Review speakers' presentations | 2021-09-17 | 3 | 2021-09-21 | 30%
P | Post-event | 2021-09-27 | 5 | 2021-10-01
T | Send out "Thank you for attending" message | 2021-09-27 | 2 | 2021-09-28
T | Send out survey | 2021-09-29 | 1 | 2021-09-29
T | Create final reports | 2021-09-30 | 2 | 2021-10-01

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (P3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TYPE, TASK NAME, START DATE, the number of WORKDAYS, and TEAM MEMBER.
|  |  | Note: | Type can be Phase (P) or Task (T).
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 24), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AV-AZ)
|  |  | Step 2: | Select the column after the last date (BA), then right click and select Insert Copied Cells.
Calculation for END DATE
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.
|  |  | Note: | Do not enter end dates manually since the END DATE is a calculated column.
Calculation for Phases
| • | You can enter the start date and number of workdays of a Phase manually.
| • | However, if you want to do calculation automatically based on its tasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_tasks_start_dates)
|  |  | WORK DAYS |  | =IF(ISBLANK(phase_start_date),"",NETWORKDAYS(phase_start_date,MAX(range_of_its_tasks_end_dates)))